## Sheet1
ID | Job Name | Additional Task | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date | Assigned People | Actual Completion % | No. of Additional Tasks | Planned Actual Start Diff. | Target Job Req Days | Actual Job Days | Target Actual Job Days Difference | Job Completion Performance (%) | Planned Remaining Days | Elapsed Days | Completion Status | Expeted Completion (%) | Target Actual Job Days Difference(in progress) | Target Actual Job Days Difference (comp/not start) | Is Completed | Early | Delayed | Late | Very Early | In Progress | On Time
1 | Talent landscape (2021 onwards) | Gender information to be added, Grade layers to be populated, Open positions month on month view, Year and month filters to be added, Consolidated overview of all KPIs to be established | 2021-01-01 | 2021-01-05 | 2021-08-15 | 2021-07-29 | Rana Usman | 100 | 4 | 4 | 226 | 205 | 21 | 9.29 | Completed | 205 | Early | Completed | 21 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0
2 | People data pipeline and insights | Pipeline yet to be established, IT dependency for the flow of information | 2021-01-01 | 2021-01-01 | 2021-08-31 | 2021-12-15 | Muhammad Zubair | 40 | 1 | 0 | 242 | 348 | -106 | -43.78 | Completed | 348 | Delayed | Completed | -106 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0
3 | Rewards data enablement on VM | Dependent on the above data pipeline | 2021-08-01 |  | 2021-08-31 |  | Muhammad Zubair | 10 | 0 | Not Started | 30 | Not Started | Not Started | Not Started | 5 | 0 | Not Started | Not Started |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | L&D data pipeline creation and valuation |  | 2021-08-17 | 2021-08-17 | 2021-09-10 |  | Rana Usman | 0 | 0 | 0 | 24 | Not Completed | Not Completed | Not Completed | 15 | 9 | In progress | 37.5 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
5 | Jazz pulse |  | 2021-08-01 | 2021-08-01 | 2021-08-31 |  | Rana Usman | 60 | 0 | 0 | 30 | Not Completed | Not Completed | Not Completed | 5 | 25 | In progress | 83.33 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
6 | Employee leaves overview |  | 2021-07-20 | 2021-07-20 | 2021-08-10 | 2021-08-08 | Rana Usman | 100 | 0 | 0 | 21 | 19 | 2 | 9.48 | Completed | 19 | Early | Completed | 2 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0
7 | People planning |  | 2021-07-20 | 2021-07-20 | 2021-09-30 |  | Muhammad Zubair | 50 | 0 | 0 | 72 | Not Completed | Not Completed | Not Completed | 35 | 37 | In progress | 51.39 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
8 | Coorelation of people variables |  | 2021-11-01 |  | 2021-12-31 |  | Rana Usman | 0 | 0 | Not Started | 60 | Not Started | Not Started | Not Started | 127 | 0 | Not Started | Not Started |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Recognition insights deployment |  | 2021-08-10 | 2021-08-10 | 2021-08-31 |  | Rana Usman | 20 | 0 | 0 | 21 | Not Completed | Not Completed | Not Completed | 5 | 16 | In progress | 76.19 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
10 | Joiners / Leavers dashboard |  | 2021-08-06 | 2021-08-06 | 2021-08-06 | 2021-08-06 | Muhammad Zubair | 100 | 0 | 0 | 0 | 0 | 0 | 0 | Completed | 0 | On Time | Completed | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1
11 | TurnOver Insights |  | 2021-07-01 | 2021-07-01 | 2021-08-31 |  | Muhammad Zubair | 0 | 0 | 0 | 61 | Not Completed | Not Completed | Not Completed | 5 | 56 | In progress | 91.8 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
12 | Analytics Management Tool |  | 2021-10-01 |  | 2021-12-01 |  | New Joiner x | 0 | 0 | Not Started | 61 | Not Started | Not Started | Not Started | 97 | 0 | Not Started | Not Started |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Analytics Goverance |  | 2021-10-01 |  | 2021-12-15 |  | New Joiner y | 0 | 0 | Not Started | 75 | Not Started | Not Started | Not Started | 111 | 0 | Not Started | Not Started |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Redefine Access Learning P&O/Business |  | 2021-09-01 |  | 2021-09-15 |  | New Joiner y | 0 | 0 | Not Started | 14 | Not Started | Not Started | Not Started | 20 | 0 | Not Started | Not Started |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | KPI Creation Around People Data |  | 2021-08-30 |  | 2021-09-25 |  | New Joiner x | 0 | 0 | Not Started | 26 | Not Started | Not Started | Not Started | 30 | 0 | Not Started | Not Started |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | L&D Analytics |  | 2021-09-01 |  | 2021-10-05 |  | New Joiner y | 0 | 0 | Not Started | 34 | Not Started | Not Started | Not Started | 40 | 0 | Not Started | Not Started |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Payroll Overview |  | 2021-09-01 |  | 2021-10-01 |  | New Joiner y | 0 | 0 | Not Started | 30 | Not Started | Not Started | Not Started | 36 | 0 | Not Started | Not Started |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | D&I Analytics |  | 2021-09-15 |  | 2021-09-30 |  | New Joiner x | 0 | 0 | Not Started | 15 | Not Started | Not Started | Not Started | 35 | 0 | Not Started | Not Started |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Data Model Development |  | 2021-08-15 | 2021-08-15 | 2021-09-01 |  | New Joiner y | 20 | 0 | 0 | 17 | Not Completed | Not Completed | Not Completed | 6 | 11 | In progress | 64.71 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
20 | Workforce Planning Monthly Progression |  | 2021-08-01 | 2021-08-01 | 2021-09-15 |  | New Joiner x | 65 | 0 | 0 | 45 | Not Completed | Not Completed | Not Completed | 20 | 25 | In progress | 55.56 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
21 | Payroll Data Pipeline |  | 2021-08-10 | 2021-08-10 | 2021-09-20 |  | New Joiner y | 40 | 0 | 0 | 41 | Not Completed | Not Completed | Not Completed | 25 | 16 | In progress | 39.02 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
22 | People Analytics Branding |  | 2021-08-10 | 2021-08-10 | 2021-09-21 |  | New Joiner y | 58 | 0 | 0 | 42 | Not Completed | Not Completed | Not Completed | 26 | 16 | In progress | 38.1 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
23 | Reward Overviews |  | 2021-08-15 | 2021-08-15 | 2021-09-05 |  | New Joiner x | 30 | 0 | 0 | 21 | Not Completed | Not Completed | Not Completed | 10 | 11 | In progress | 52.38 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
24 | Divisional Champ Insight |  | 2021-08-15 | 2021-08-15 | 2021-09-30 |  | New Joiner y | 80 | 0 | 0 | 46 | Not Completed | Not Completed | Not Completed | 35 | 11 | In progress | 23.91 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
25 | Pulse Check Review |  | 2021-08-10 | 2021-08-10 | 2021-10-01 |  | New Joiner y | 55 | 0 | 0 | 52 | Not Completed | Not Completed | Not Completed | 36 | 16 | In progress | 30.77 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
26 | Turnover Insights | A, B, C, D | 2021-08-10 | 2021-08-10 | 2021-10-01 |  | New Joiner x | 60 | 3 | 0 | 52 | Not Completed | Not Completed | Not Completed | 36 | 16 | In progress | 30.77 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
27 | Advanced Talent Landscape |  | 2021-08-17 | 2021-08-17 | 2021-10-15 |  | New Joiner x | 2 | 0 | 0 | 59 | Not Completed | Not Completed | Not Completed | 50 | 9 | In progress | 15.25 |  | Not Completed | 0 | 0 | 0 | 0 | 0 | 1 | 0
28 | Sales Competition 2.0 KYSF |  | 2021-01-20 | 2021-01-20 | 2021-04-20 | 2021-04-03 | New Joiner y | 100 | 0 | 0 | 90 | 73 | 17 | 18.87 | Completed | 73 | Very Early | Completed | 17 |  | 1 | 0 | 0 | 0 | 1 | 0 | 0
29 | Amazon Redshift Talent Pipeline |  | 2021-06-01 | 2021-06-01 | 2021-07-01 | 2021-07-04 | New Joiner y | 100 | 0 | 0 | 30 | 33 | -3 | -9.97 | Completed | 33 | Late | Completed | -3 |  | 1 | 0 | 0 | 1 | 0 | 0 | 0
31 | Exit Data Pipeline |  | 2021-07-01 | 2021-07-01 | 2021-08-15 | 2021-08-01 | New Joiner x | 100 | 0 | 0 | 45 | 31 | 14 | 31.04 | Completed | 31 | Very Early | Completed | 14 |  | 1 | 0 | 0 | 0 | 1 | 0 | 0
32 | Preliminary Talent Landscape |  | 2021-06-15 | 2021-06-15 | 2021-07-01 | 2021-07-01 | New Joiner x | 100 | 0 | 0 | 16 | 16 | 0 | 0 | Completed | 16 | On Time | Completed | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1
33 | D&I Baseline KPI's Marking |  | 2021-06-20 | 2021-06-20 | 2021-07-30 | 2021-07-30 | New Joiner y | 100 | 0 | 0 | 40 | 40 | 0 | 0 | Completed | 40 | On Time | Completed | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1
34 | People Data Model Schema Creation |  | 2021-06-01 | 2021-06-01 | 2021-06-20 | 2021-06-20 | New Joiner y | 100 | 0 | 0 | 19 | 19 | 0 | 0 | Completed | 19 | On Time | Completed | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1
35 | Oracle Data Pipeline Exploration |  | 2021-06-20 | 2021-06-20 | 2021-07-01 | 2021-06-30 | New Joiner x | 100 | 0 | 0 | 11 | 10 | 1 | 9.01 | Completed | 10 | Early | Completed | 1 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0
36 | Talent Dashboard Creation |  | 2021-06-10 | 2021-06-10 | 2021-07-30 | 2021-07-25 | New Joiner y | 100 | 0 | 0 | 50 | 45 | 5 | 9.98 | Completed | 45 | Early | Completed | 5 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0
37 | Wellness Pulse Check |  | 2021-07-01 | 2021-07-01 | 2021-07-10 | 2021-07-15 | New Joiner x | 100 | 0 | 0 | 9 | 14 | -5 | -54.95 | Completed | 14 | Delayed | Completed | -5 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0
38 | Title Analytics |  | 2021-07-05 | 2021-07-01 | 2021-08-15 | 2021-08-30 | New Joiner y | 100 | 0 | -4 | 41 | 60 | -19 | -46.23 | Completed | 60 | Delayed | Completed | -19 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0
39 | TSS Retention Analytics |  | 2021-07-01 | 2021-07-01 | 2021-08-07 | 2021-08-03 | New Joiner y | 100 | 0 | 0 | 37 | 33 | 4 | 10.78 | Completed | 33 | Very Early | Completed | 4 |  | 1 | 0 | 0 | 0 | 1 | 0 | 0
40 | Joiner/Leaver Dashboard | Z, B | 2021-07-10 | 2021-07-11 | 2021-08-10 | 2021-08-09 | New Joiner x | 100 | 1 | 1 | 31 | 29 | 2 | 6.43 | Completed | 29 | Early | Completed | 2 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0
41 | Performance Pulse Check |  | 2021-08-10 | 2021-08-10 | 2021-08-25 | 2021-08-20 | New Joiner x | 100 | 0 | 0 | 15 | 10 | 5 | 33.11 | Completed | 10 | Very Early | Completed | 5 |  | 1 | 0 | 0 | 0 | 1 | 0 | 0
Formulas:
Planned Actual Start Diff. = IF(ISBLANK([Actual Start Date]),"Not Started",IF([Actual Start Date]<[Planned Start Date],DATEDIF([Actual Start Date],[Planned Start Date],"d")*-1,DATEDIF([Planned Start Date],[Actual Start Date],"d")))
Target Job Req Days = DATEDIF([Planned Start Date],[Planned End Date],"d")
Actual Job Days = IF([Planned Actual Start Diff.]="Not Started","Not Started",IF(NOT([Actual End Date]),"Not Completed",DATEDIF([Actual Start Date],[Actual End Date],"d")))
Planned Remaining Days = IF(ISNUMBER([Job Completion Performance (%)]),"Completed",DAYS([Planned End Date],TODAY()))
Elapsed Days = IF(OR([Planned Remaining Days]="Completed",[Planned Actual Start Diff.]="Not Started"),DAYS([Actual End Date],[Actual Start Date]),DAYS(TODAY(), [Actual Start Date]))
Expeted Completion (%) = IF([Completion Status]="Not Started","Not Started",IF(NOT([Completion Status]="In progress"),"Completed",ROUND((100/[Target Job Req Days])*(DAYS(TODAY(),[Planned Start Date])),2)))